# Meeting Notes — Term 1 Materials Revision Planning

# Meeting Notes

Meeting: Term 1 RISE FLP Materials Revision — Roll-Out Preparation Date: 12 May 2026 Presided by: Director Jeng, MoBSE / CREDD Participants: LM Technical Team; Language Group Desk Officers and Selected Writers

## Background and Opening

The meeting was convened and opened by Director Jeng, who communicated key strategic decisions regarding the RISE FLP Term 1 materials. Director Jeng subsequently handed over to the LM Technical Team to work through the operational details of the new plan with his technical staff.

## Key Decisions Communicated by Director Jeng

- The September 2026 pilot has been shelved. September 2026 will now be a full national roll-out period, not a pilot.

- The roll-out will use the developed Term 1 materials, which must be revised to incorporate: (a) observations from the Codification Team (national languages), and (b) harmonization feedback.

- The hard deadline for completing the revision is 5 June 2026, to allow adequate printing and shipping time before the September school session.

- The already-printed Term 1 materials will not be used for roll-out; they will serve as supplementary materials only.

## Proposed Activity Calendar

| Date | Activity |
| --- | --- |
| 13 May 2026 (Wed) | Planning Day — Prepare all source materials for language group teams |
| 14–22 May 2026 (Thu–Fri) | Activity Days — Language groups review Term 1 materials; Layout Designers begin 20 May |
| 25–29 May 2026 | Break — Tobaski Holiday Period |
| 1–5 June 2026 | Activity Days — Review design layouts; finalize and submit all materials |

Note: Illustrator requirements and scheduling will be determined during the review period.

## Personnel Requirements

- National Language groups: Each represented by the Desk Officer + 2 additional members drawn from the group based on strengths

- English group: Desk Officer + 5 additional members given the wider scope of work

## Selected Writers by Language Group

### English

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Philomen Sanyang (Desk Officer) | Grade 1 | CREDD |
| 2 | Modou A. Sambou | Grade 1 | CREDD |
| 3 | Kumba Bah | ECD 3 | CREDD |
| 4 | Fanny Njie | ECD 2 | ECD Unit |
| 5 | Buba Marreh | ECD 3 | INSET |
| 6 | Michelle Rose Mendy | ECD 2 | CREDD |

### Jola

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Saffie Camara (Desk Officer) | Grade 1 | CREDD |
| 2 | Amidou Antieng Jarjue | Grade 1 | Retired, Region 2 East |
| 3 | Pa Ansu Camara | ECD 3 | Kampasa LBS |

### Mandinka

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Lamin B. Jammeh (Desk Officer) | ECD 2 | Retired |
| 2 | Ansu Sanyang | ECD 3 | CREDD |
| 3 | Sirra Faye | Grade 1 | Bundung Annex LBS |

### Manjaku

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Victoria Gomez (Desk Officer) | ECD 2 | CREDD |
| 2 | John Bass | ECD 2 | Retired |
| 3 | Daniel J. Mendy | ECD 3 | TBD |

### Pulaar

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Adama Barry (Desk Officer) | — | CREDD |
| 2 | Amadou Khan | Grade 1 | — |

### Soninke

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Surakata Susso (Acting Desk Officer) | Grade 1 | — |

### Seereer

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Maget Sarata Njie | ECD 3 | CREDD |
| 2 | Marong Madun N. | Grade 1 | INSET |
| 3 | Bintou Corr | ECD 3 | Old Jeshweng LBS |

### Wolof

| # | Name | Sub-group | Posting |
| --- | --- | --- | --- |
| 1 | Adama Jaye (Desk Officer) | ECD 3 | CREDD |
| 2 | Biran Gai | Grade 1 | PMED |
| 3 | Amie Bittaye | Grade 1 | Banjul, St. Mary’s |

Notes compiled by: LM Technical Team | Distribution: Director Jeng, Zahra Maishanu, Desk Officers