# Post-Jerreh Camp Activities Schedule: RISE FLP Term 2 & 3 Planning

May - July 2026

RISE FLP / Learning Matters | April 2026

# Schedule: Term 3 Material Development

Activity: Term 3 Material Development Workshop

Timeline: June 7 - July 5, 2026 (4 weeks)

Lead/Focal Point: LM Team, CREDD, Language Groups

| Activity | Timeline | Lead/Focal Point |
| --- | --- | --- |
| Review and Finalize Term 2 Materials | May 4 - 8, 2026 | Language Groups & LM Team |
| Illustration of Term 2 Materials | May 4 - 8, 2026 (plus potential extension) | Illustration Team |
| Codification Review (Term 1 Completion & Term 2) | May 11 - 22, 2026 | Codification Team & Desk Officers |
| Layout Design of Term 2 Materials | May 18 - 29, 2026 | Layout & Design Team |
| Compilation, Collation & Final Hand-off to MoBSE | June 1 - 5, 2026 | LM Team & CREDD |

# Key Considerations for MoBSE Planning

To ensure the smooth execution of the upcoming activities, please consider the following points for planning purposes:

Codification Team Composition: To prevent the bottlenecks experienced previously, we recommend that each Desk Officer be supported by two members from their respective language teams (one representing Grade 1 and one representing ECD). This will distribute the workload and enhance the quality of the review.

English Language Material Review: A dedicated team should be composed to review the English Language materials. This team's mandate will be to ensure quality, consistency, and full compliance with the agreed-upon harmonization standards.