# Decodability Review System Plan for RISE FLP

Updated Plan for Pulaar and Mandinka EGR Materials

Hermes Agent / RISE FLP | April 2026

# Introduction

This document outlines the updated plan for the decodability review system for Early Grade Reading (EGR) materials in The Gambia, focusing on Grade 1 texts for Pulaar and Mandinka. The plan incorporates feedback on manual discrepancy handling, a focused testing scope, and exclusion of English materials.

## Key Updates Based on Feedback

1. Discrepancy Handling: Discrepancies in teaching sequences will be addressed manually by linguists, supported by detailed system-generated reports.
2. Testing Scope: Testing will cover a 2-week scope of work for two languages with complex orthographies, Pulaar and Mandinka.
3. Exclusion of English: English EGR materials and harmonization with EI standards are excluded from this exercise.

## Revised Plan with Interlinked Steps

The following steps are designed to ensure a cohesive workflow for the decodability review system.

### Step 1: Refinement of Reference Standards

Objective: Ensure all reference materials are up-to-date and accessible.
Action: Verify ingestion of the master reference 'Language_Descriptions_FLP_April2026.docx' in ChromaDB. Ingest supplementary orthography documents for Pulaar and Mandinka if needed.
Linkage: Forms the foundation for Steps 2 and 3.
Output: Confirmation of ingested documents.

### Step 2: Enhanced Discrepancy Analysis (Manual Handling)

Objective: Identify mismatches for manual correction.
Action: Use the 'egr-document-review' skill to flag discrepancies in Pulaar and Mandinka teaching sequences, generating detailed reports for linguists.
Linkage: Builds on Step 1 data and feeds into Step 4 for testing.
Output: Discrepancy reports stored in /root/.hermes/output/.

### Step 3: Decodability Model Optimization

Objective: Refine decodability metrics for selected languages.
Action: Adjust the model in the 'egr-document-review' skill for Pulaar and Mandinka, focusing on a 2-week teaching scope.
Linkage: Uses Step 1 references and prepares for Step 4 testing.
Output: Updated model parameters.

### Step 4: Testing Phase (2-Week Scope)

Objective: Validate the model with sample materials.
Action: Review texts from a 2-week scope for Grade 1 Term 1 in Pulaar and Mandinka using the optimized model.
Linkage: Tests Step 3 model with Step 2 insights, results feed into Step 5.
Output: Test results logged in /root/.hermes/logs/rise_flp_log.md.

### Step 5: Review Protocol Formalization and Reporting

Objective: Formalize the review process and produce reports.
Action: Embed a three-step protocol in the skill: orthographic compliance, sequence alignment, and report generation using 'generate_word_document'. Focus on Pulaar and Mandinka only.
Linkage: Integrates outputs from Steps 2, 3, and 4 for final deliverables.
Output: Final review report in Word format.

## Implementation Details

Tools Used: ChromaDB ingestion and search tools, Word document generation.
Skill Updates: Enhance 'egr-document-review' skill for the interlinked workflow.
Focus: Prioritize Grade 1 Term 1 materials for Pulaar and Mandinka.